## Start here
Talum 1 (T11) — first cast: what to measure and record
Version 2026-10-12 · R-D-alloys knowledge base · results go into knowledge/trials/T11.md §4
Every value in this file calibrates the alloy models: solidification and Fe phases, recrystallisation and grain size, natural ageing, press force, can strength, surface oxide (MgO). Record what actually happened, not the targets.
How to use
1. Plan — the checklist. Do all A rows; B if time allows. Set Status and Who.
2. Chemistry — one row per spectrometer sample. Out-of-spec T11 values turn red.
3. Process log — one column per coil (T11 and the reference alloy). Grey cells calculate themselves.
4. Results — one row per single reading. Pick the Plan ID; name and unit fill in.
5. Send the file back. The data go into the T11 record and the model calibration.
Rules that make the data usable
1. Actual values with date and time. Slug age and can age are calculated from them.
2. Enter every single reading, not only the mean. The models need the scatter.
3. Same method for T11, REF and every repeat (same Brinell ball and load; conductivity at 20 °C or compensated).
4. Run the reference alloy (current production) through the same steps and tests in the same week.
5. Never delete odd results or failures; add a comment.
6. Name photos and logger files with the Sample ID.
Sample ID = Alloy-Cast-Coil-Stage-No.
Example: T11-C1-K2-SL-03 = Talum 1, cast 1, coil 2, annealed slug no. 3.
Stage codes: CH chemistry · CS cast strip · HB hot band · CR cold-rolled strip · LA lab-annealed slug · SL annealed slug · EX extruded can · CN baked can.
Position (Results): surface · quarter · centre · edge · full section.
Trial variants (if the line allows)
Slug anneal: air vs N₂, each with normal furnace cooling vs faster cooling → 4 slug lots.
Hot/cold split: all coils at the current split. Optional: one coil with more cold reduction (ε_cold ≈ 0.85–0.90, hot band ≈ 14–18 mm). This needs < 50 % hot reduction, so only if the mill allows it.
Write the variant in Process log (row "Trial variant") and in Results (column "Variant").
Timeline
Day 0: melt, cast, hot roll, quench → Chemistry, Process log, cast-strip and hot-band samples.
Days 0–7: hot-band hardness at 0, 1, 3, 7 days (HB02) → cold rolling → slugs.
Anneal day: thermocouple log; slug hardness at 2–6 h, then 1, 3, 7, 30 days (SL01).
Lab: anneal series (LA01), metallography, conductivity.
Press: force with slug age, rejects, wall thickness. Bake 220 °C / 10 min: can tests 1 and 30 days after.
Example Results rows (example values, not predictions)
| Date | Sample ID | Alloy | Plan ID | Position | Variant | Age (h) | Value
| 2026-10-21 | T11-C1-K1-SL-01 | T11 | SL01 | full section | air, furnace cool | 4 | 29.5
| 2026-10-22 | T11-C1-K1-SL-01 | T11 | SL01 | full section | air, furnace cool | 24 | 30.1
| 2026-10-21 | T11-C1-K1-SL-02 | T11 | SL02 | centre | air, furnace cool |  | 64
| 2026-10-20 | T11-C1-K1-LA-01 | T11 | SL01 | full section | lab 350 °C 1 h |  | 41

## Plan
Measurement plan — Talum 1 (T11)
Priority A = must, B = should. Ref = section or rule in the knowledge base.
ID | Stage | What to measure | Unit | Method / instrument | Where & when | Samples | Prio | Model it feeds | Why it matters | Ref | Record in | Status | Who
G01 | General | Reference alloy: run the current production alloy through the same steps and tests in the same week | – | Same as T11 | All stages, at least from the slug anneal on | Same as T11 | A | Baseline | Gives a direct T11 vs REF difference on the same furnace, press and day; removes line and day effects | T11 §3 | All sheets (Alloy = REF) | open
G02 | General | Event log: stops, strip breaks, temperature excursions, setting changes, with clock time | text | Operator log | Whole trial | – | A | All | Lets the model explain or exclude outliers instead of learning noise | – | Process log (Events row) | open
G03 | General | Retained samples of every stage, labelled with Sample ID | – | Storage | ≥ 1 m cast strip, ≥ 1 m hot band, ≥ 1 m as-rolled, 30 slugs and 30 cans per variant | – | A | All | Later tests (EBSD, XPS, extra ageing points) without a new cast | – | – | open
CH1 | Chemistry | Melt chemistry before and after correction | wt % | OES spark spectrometer | Furnace, every sample | All | A | Scrap blend | Element recovery (Fe, Mn, Ti yield) and Mg burn-off for the scrap-mix model | ch16 | Chemistry | open
CH2 | Chemistry | Cast chemistry | wt % | OES spark spectrometer | Cast start, middle, end | 3 per cast | A | All models | The actual composition is the model input, not the target | T11 §1 | Chemistry | open
CH3 | Chemistry | Through-thickness chemistry of the cast strip | wt % | OES on the strip surface and on strip milled to mid-thickness | Mid-cast | 1 + 1 | B | Solidification | Centreline (Fe-rich) segregation on the rotary caster | ch15; T11 §2.3 | Chemistry | open
P1 | Process | Melt: charge weights, furnace and launder temperatures, hydrogen, grain-refiner feed and contact time | various | Charge sheet, thermocouple, hydrogen / density test | Per cast | – | A | Scrap blend; Solidification | Refiner dose sets cast grain size and α vs β Fe phase; melt temperature sets superheat | ch02 §3.8 | Process log | open
P2 | Process | Caster: speed, strip thickness and width, cooling-water flow and temperatures, strip exit temperature, cracks | various | Caster log, pyrometer | Continuous; note start, middle, end | – | A | Solidification; Castability | Speed and water set the cooling rate → cell size and Fe-phase type; cracks show the hot-tear limit | ch15; ch01 §11 | Process log | open
P3 | Process | Hot mill and bath: thickness in/out, temperatures in/out, speed, force, transfer times, bath and post-bath temperature | various | Mill log, pyrometer | Per coil | – | A | Hot flow; RX / grain size | Force at known temperature and strain rate calibrates the hot flow law; the bath sets retained solute | R24; ch19 §1.3 | Process log | open
P4 | Process | Cold mill: thickness per pass, force, exit temperature; hot-band storage time | various | Mill log | Per coil | – | A | RX / grain size; Ageing | Cold strain sets stored energy and the number of RX nuclei → grain size | R14; ch19 P10 | Process log | open
P5 | Process | Slug anneal: furnace, load, atmosphere, full temperature–time log from thermocouples in the slugs | °C vs time | Thermocouple logger, load centre and edge | Every load | – | A | RX / grain size; Ageing; Surface | Heating rate shifts the RX temperature (up to ≈ 75 °C in Al–Mn); cooling rate decides Mg₂Si in solution vs precipitated | ch03 §5.2; T11 §2.3 | Process log + logger file | open
P6 | Process | Press: press and tool set, strokes/min, lubricant and amount, extrusion and bake dates | text | Press log | Per lot | – | A | Press force | Context for force and reject data; dates give slug and can age | ch10 | Process log | open
CS01 | Cast strip | Cell / dendrite arm spacing (surface, quarter, centre) | µm | Optical metallography, line intercept | Mid-cast, full-thickness section | 1 section | A | Solidification | Measures the local cooling rate; sets the homogenisation time (τ ∝ l²) | ch19 §1.1 | Results | open
CS02 | Cast strip | Fe-particle type: share of β-AlFeSi (needles) among Fe-rich particles | % by count | SEM-EDX, α/β separator Si ≈ 0.48·(Fe+Mn) | Surface and centre | ≥ 100 particles each | A | Solidification | β needles are the main risk at Mn:Fe ≈ 0.27 (die wear, base-corner damage) | ch02 §3.8; R25 | Results | open
CS03 | Cast strip | Share of constituent particles > 3 µm (equivalent diameter) | % of particles | SEM or optical image analysis | Surface and centre | ≥ 500 particles | A | RX / grain size | Only particles ≳ 3–7 µm nucleate grains at this cold strain (PSN) → slug grain size | R14; ch03 §3.2b | Results | open
CS04 | Cast strip | Constituent particle area fraction | % | Image analysis (same images as CS03) | Surface and centre | Same images | B | RX / grain size | Zener pinning and PSN density | R12 | Results | open
CS05 | Cast strip | Electrical conductivity | MS/m | Eddy current at 20 °C (or compensated) | Mid-cast | 5 readings | A | Solidification; Ageing | Baseline of solute in solution (Mn, Fe, Si, Mg) | ch13; ch19 P9 | Results | open
CS06 | Cast strip | Macro-etch: centreline segregation, porosity, cracks | grade 0–3 + photo | Macro etch of the cross section | Cast start, middle, end | 3 | A | Castability | Hot-tearing and segregation risk from Mg + Si | ch01 §11; ch15 | Results | open
CS07 | Cast strip | Cast grain size | µm | Barker anodising + polarised light | Surface and centre | 1 section | B | Solidification | Grain-refiner response | ch01 | Results | open
HB01 | Hot band | Conductivity after the bath | MS/m | Eddy current | Per coil | 5 readings | A | Ageing; RX / grain size | Solute retained by the quench | ch19 §1.3 | Results | open
HB02 | Hot band | Hardness vs storage time: 0, 1, 3, 7 days and at cold rolling | HB | Brinell, same ball and load throughout | Per coil; enter Age (h) | 3 indents | B | Ageing | Natural ageing of the quenched band before cold rolling | ch04 §6; T11 §2.4 | Results | open
HB03 | Hot band | Structure: recrystallised or recovered; grain size | µm | Barker + polarised light (EBSD optional) | Full thickness | 1 section | B | RX / grain size | Starting structure for cold rolling | ch19 §1.3 | Results | open
CR01 | Cold rolled | Hardness as rolled | HB | Brinell | Per coil | 3 indents | A | Press force; RX / grain size | Work-hardening point; proxy for stored energy | ch10 §3.4 | Results | open
CR02 | Cold rolled | Conductivity as rolled | MS/m | Eddy current | Per coil | 5 readings | A | RX / grain size | Solute state just before the anneal | ch19 P9 | Results | open
CR03 | Cold rolled | Tensile Rp0.2, longitudinal | MPa | Tensile test | Per coil | 3 | B | Can strength | Work-hardening curve vs Ryen data | ch10 §3.4 | Results | open
CR04 | Cold rolled | Tensile Rm, longitudinal | MPa | Tensile test | Per coil | 3 | B | Can strength | Work-hardening curve vs Ryen data | ch10 §3.4 | Results | open
LA01 | Lab anneal | Lab anneal series on as-rolled slugs: 250–550 °C in 50 °C steps, 1 h; repeat two temperatures with fast heating | – | Lab furnace; salt bath or pre-heated furnace for fast heating | Enter results as SL01, SL04, SL05 with Variant = e.g. "lab 400 °C 1 h" | 7 temperatures × 2 slugs | A | RX / grain size | The softening curve is the main calibration of the RX model and finds the lowest safe anneal temperature (less MgO) | ch03; ch19 P3/P4 | Results | open
SL01 | Annealed slug | Hardness | HB | Brinell, same ball and load always | 2–6 h, 1, 3, 7, 30 days after the anneal; enter Age (h) | 5 slugs × 3 indents | A | Ageing; Press force | Natural-ageing drift → press-force drift (Mg + Si in solution) | ch04 §6.5; R21, R22 | Results | open
SL02 | Annealed slug | Mean grain size | µm | Barker + polarised light, linear intercept | Surface and centre of a slug section | 3 slugs | A | RX / grain size | Target 20–100 µm; main output of the RX / PSN model | R14; ch03 | Results | open
SL03 | Annealed slug | Grain-size scatter: largest grain or standard deviation | µm | Same images as SL02 | Surface and centre | 3 slugs | B | RX / grain size | Coarse or mixed grains → orange peel and tearing | ch10 | Results | open
SL04 | Annealed slug | Recrystallised fraction | % | Same images as SL02 | Surface and centre | 3 slugs | A | RX / grain size | Should be 100 %; below that the anneal is too low or too short | R22; ch03 | Results | open
SL05 | Annealed slug | Conductivity | MS/m | Eddy current | Per lot | 5 slugs | A | Ageing; RX / grain size | Tracks Mg, Si and Mn going into or out of solution in the anneal | ch19 P9 | Results | open
SL06 | Annealed slug | Surface oxide: colour / wipe grade; thickness on a subset | grade 0–3; nm | Visual + wipe test; GDOES or XPS on a subset | Air vs N₂ lots | 5 + 1 | B | Surface (MgO) | Mg 0.26 is about 2× the in-house alloys; decides air vs N₂ | R18; ch14 | Results | open
SL07 | Annealed slug | Compression flow stress at true strain 1.0 | MPa | Lubricated upsetting test | Per lot | 3 | B | Press force | Large-strain flow stress predicts press force better than HB | R21; ch10 | Results | open
SL08 | Annealed slug | Wall simulation: roll slug material to ε ≥ 2, then 220 °C / 10 min; HV before, 1 and 30 days after | HV | Lab rolling + oven | Per lot; Variant = unbaked / baked; enter Age (h) | 3 × 3 | B | Can strength | Bake response (strain ageing) without running the press | ch19 P6; T11 §3 | Results | open
EX01 | Extrusion | Maximum press force (mean of ≥ 100 strokes), with slug age | t | Press load monitor | Per lot; enter slug Age (h) | ≥ 100 strokes | A | Press force | Calibrates force vs HB and flow stress (35 HB ≈ 391 t estimate for a flat Ø53 punch) | R21 | Results | open
EX02 | Extrusion | Wall thickness at mid-height | mm | Micrometer | Per lot | 10 cans | A | Can strength | Sets the wall strain for the strength model | ch10 | Results | open
EX03 | Extrusion | Reject rate: tears, splits, base-corner cracks, orange peel | % | Inspection | Per lot | Whole lot | A | Press force; Castability | Extrudability (design goal 2) | ch10 §5 | Results | open
EX04 | Extrusion | Base-corner section after extrusion and after necking | finding + photo | Metallography | Per lot | 3 cans | B | Solidification | Hidden damage from coarse Fe particles | R23; ch10 §5 | Results | open
K01 | Can | Wall Rp0.2, longitudinal (Variant = unbaked / baked) | MPa | Tensile test | Before and 1 day after 220 °C / 10 min | 3 cans each | A | Can strength | The strength target; compare with Ryen (1050 vs 3103 can walls) | ch10 §3.4 | Results | open
K02 | Can | Wall Rm, longitudinal (Variant = unbaked / baked) | MPa | Tensile test | Before and 1 day after the bake | 3 cans each | A | Can strength | The strength target | ch10 §3.4 | Results | open
K03 | Can | Wall elongation A | % | Tensile test | Before and 1 day after the bake | 3 cans each | B | Can strength | Ductility left for necking and shaping | ch10 | Results | open
K04 | Can | Burst pressure | bar | Burst tester | After the bake | ≥ 10 cans | A | Can strength | Customer KPI; burst ≥ 1.2 × test pressure | R19 | Results | open
K05 | Can | Deformation (dome-reversal) pressure | bar | Pressure tester | After the bake | ≥ 10 cans | A | Can strength | Customer KPI; test ≥ 10 bar or 1.5 × P(50 °C) | R19 | Results | open
K06 | Can | Necking / shaping rejects | % | Line count | Per lot | Whole lot | A | Can strength | Formability after the bake | ch10 | Results | open
K07 | Can | Wall hardness 1 and 30 days after the bake | HV | Micro-hardness | Enter Age (h) after the bake | 3 cans | B | Ageing | Ageing after the bake | ch04 §6 | Results | open
K08 | Can | Internal lacquer porosity / adhesion | mA / grade | Enamel rater; cross-cut test | After the bake | 10 cans | B | Surface (MgO) | Oxide effect on the coating | ch14 | Results | open

## Chemistry
Chemistry — every spectrometer sample (wt %)
Enter ppm elements as wt % (5 ppm = 0.0005). Red = T11 sample outside the T11 window. Mn/Fe ≥ 0.5 favours compact α; Fe/Si > 1 avoids free Si, ≥ 2 avoids β.
Sample ID | Alloy | Cast no. | Sample point | Date / time | Si | Fe | Mn | Mg | Cu | Ti | Zn | Cr | Ni | V | Zr | B | Ga | Na | Ca | Pb | Sn | Mn/Fe | Fe/Si | Mg/Si | Notes
T11 target |  |  |  |  | Si: 0.38; Fe: 0.52; Mn: 0.14; Mg: 0.26; Cu: 0.038; Ti: 0.043; Zn: 0.034; Cr: 0.011
T11 min |  |  |  |  | Si: 0.37; Fe: 0.51; Mn: 0.13; Mg: 0.24
T11 max |  |  |  |  | Si: 0.39; Fe: 0.53; Mn: 0.15; Mg: 0.28; Cu: 0.042; Ti: 0.05; Zn: 0.05; Cr: 0.03
T11-C1-CH-FB | T11 | C1 | Furnace before correction
T11-C1-CH-FF | T11 | C1 | Furnace final
T11-C1-CH-CS | T11 | C1 | Cast start
T11-C1-CH-CM | T11 | C1 | Cast middle
T11-C1-CH-CE | T11 | C1 | Cast end
T11-C1-CH-SS | T11 | C1 | Strip surface
T11-C1-CH-SC | T11 | C1 | Strip centre
REF-C1-CH-CM | REF | C1 | Cast middle

## Process log
Process log — one column per coil
Enter actual values. Grey cells calculate themselves. Melt rows: fill once per cast.
Stage | Parameter | Unit | Expected / target | T11 coil 1 | T11 coil 2 | T11 coil 3 | T11 coil 4 | REF coil 1 | REF coil 2 | Notes
ID | Alloy | – | T11 / REF | T11 | T11 | T11 | T11 | REF | REF
ID | Cast no. | –
ID | Coil no. | – |  | K1 | K2 | K3 | K4 | K1 | K2
ID | Casting date and time | date
ID | Trial variant | text | split; anneal atmosphere; cooling
Melt | T11S scrap charged | kg | ≈ 3,460 per 10 t (weigh-in)
Melt | 1xxx scrap charged | kg | ≈ 6,802 per 10 t
Melt | Primary or other Al charged | kg
Melt | Al-75Fe | kg | ≈ 28 per 10 t
Melt | Al-20Mn | kg | ≈ 51 per 10 t
Melt | AlTi5B1 | kg | ≈ 10 per 10 t
Melt | Metal tapped | kg
Melt | Furnace temperature at tapping | °C
Melt | Launder / tundish temperature | °C
Melt | Hydrogen or density index after degassing | ml/100 g or %
Melt | Grain-refiner rod feed rate | kg/t
Melt | Refiner contact time before the caster | min
Caster | Casting speed | m/min
Caster | Cast strip thickness | mm | 22
Caster | Strip width | mm
Caster | Cooling-water flow | m³/h
Caster | Cooling-water temperature in | °C
Caster | Cooling-water temperature out | °C
Caster | Strip temperature leaving the caster | °C | ≈ 500
Caster | Cracks / surface defects | count per 100 m | 0
Hot mill | Hot-band thickness | mm | ≤ 11 at ≥ 50 % reduction
Hot mill | Hot reduction | % | ≥ 50 % (current rule)
Hot mill | Hot true strain ε_hot | –
Hot mill | Mill entry temperature | °C | ≈ 500
Hot mill | Mill exit temperature | °C | ≈ 380
Hot mill | Exit speed | m/min
Hot mill | Rolling force | kN
Hot mill | Time caster → mill | s
Hot mill | Time mill → bath | s
Bath | Bath water temperature | °C
Bath | Strip temperature after the bath | °C
Bath | Storage time before cold rolling | h
Cold mill | Number of passes | –
Cold mill | Final (slug) thickness | mm | 6.1–7.4
Cold mill | Cold reduction | % | 30–50 % (plant)
Cold mill | Cold true strain ε_cold | – | 0.36–0.69 plant; 0.85–0.90 KB target
Cold mill | Rolling force, last pass | kN
Cold mill | Strip temperature after the last pass | °C
Slugs | Slug diameter | mm
Slugs | Slug thickness (measured) | mm
Slugs | Slug mass | g
Anneal | Furnace ID / type | text
Anneal | Load mass | kg
Anneal | Atmosphere | air / N₂
Anneal | Dew point or O₂ (N₂ only) | °C / ppm | O₂ < a few hundred ppm
Anneal | Time to soak, coldest thermocouple | min
Anneal | Soak temperature, slug thermocouple | °C
Anneal | Soak time | min
Anneal | Average heating rate | °C/min | calculated
Anneal | Cooling method | text | furnace / forced air
Anneal | Cooling time, soak → 100 °C | min
Anneal | Anneal end (date and time) | date
Anneal | Temperature–time log file name | text
Press | Press ID / tool set | text
Press | Strokes per minute | 1/min
Press | Lubricant type | text
Press | Lubricant amount | g per 1000 slugs
Press | Extrusion date and time | date
Press | Slug age at extrusion | days | calculated
Press | Bake date and time (220 °C / 10 min) | date
Events | Events and deviations (with clock time) | text

## Results
Results — one row per single reading
Pick the Plan ID; Measurement and Unit fill in. Age = hours after the anneal (slugs) or after the bake (cans).
Date | Sample ID | Alloy | Cast no. | Coil no. | Plan ID | Measurement | Unit | Position | Variant / condition | Age (h) | Value | Method / instrument | Operator | Comment / photo file

## Lists (hidden)
Results Plan ID | Position | Chemistry sample point
CS01 | surface | Furnace before correction
CS02 | quarter | Furnace final
CS03 | centre | Cast start
CS04 | edge | Cast middle
CS05 | full section | Cast end
CS06 | n/a | Strip surface
CS07 |  | Strip centre
HB01 |  | Other
HB02
HB03
CR01
CR02
CR03
CR04
SL01
SL02
SL03
SL04
SL05
SL06
SL07
SL08
EX01
EX02
EX03
EX04
K01
K02
K03
K04
K05
K06
K07
K08